## Risk Tracker
Risk Assessment Tracker
ID | Risk Name | Short Description | Manager | Probability | Impact | Risk Level
1 | Website Downtime | E-commerce site goes offline, leading to lost sales and poor customer experience. | Rafiul Islam | Rare | Negligible | Low
2 | Payment Gateway Failure | Payment system error prevents transactions, affecting revenue and trust. | Sadia Karim | Possible | Minor | Medium
3 | Data Breach | Customer data (emails, card info) exposed to hackers. | Mehedi Hasan | Unlikely | Minor | Low
4 | Delivery Delays | Logistic partners fail to deliver on time, hurting brand image. | Nusrat Jahan | Likely | Critical | Extreme
5 | Inventory Mismatch | Stock quantity errors cause overselling or order cancellations. | Fahim Reza | Very Likely | Major | Extreme
6 | Supplier Reliability | Inconsistent suppliers cause shortage in high-demand products. | Taslima Akter | Possible | Moderate | Medium
7 | Refund & Return Fraud | Customers abuse return policies leading to financial loss. | Naimul Huda | Very Likely | Major | Extreme
8 | Cyber Attack / DDoS | Malicious attacks disrupt website performance or cause downtime. | Farzana Rahman | Possible | Critical | High
9 | Poor Customer Review Surge | Negative reviews spread online, reducing trust and sales. | Tanvir Chowdhury | Possible | Negligible | Low
10 | Regulatory Non-Compliance | Failure to meet e-commerce laws, taxes, or consumer rights. | Sumiya Akter | Unlikely | Critical | High

## Scale
Risk Assessment Tracker
|  |  | Negligible | Minor | Moderate | Major | Critical
|  | Very Likely | Medium | High | High | Extreme | Extreme
|  | Likely | Medium | Medium | High | Extreme | Extreme
|  | Possible | Low | Medium | Medium | High | High
|  | Unlikely | Low | Low | Medium | Medium | High
|  | Rare | Low | Low | Low | Medium | Medium
Probability Level | Description
Very Likely | Rare chance of occurring
Likely | Unlikely but possible
Possible | Could happen occasionally
Unlikely | Likely to happen frequently
Rare | Almost certain to happen
Impact Level | Description
Negligible | Minimal impact on operations
Minor | Minor disruption, easily managed
Moderate | Noticeable impact on performance
Major | Serious disruption or financial loss
Critical | Major loss or reputation damage
Impact
Probability

## Sheet1
ID | Risk Name | Short Description | Manager | Probability | Impact | Risk Level
1 | Website Downtime | E-commerce site goes offline, leading to lost sales and poor customer experience. | Rafiul Islam | 1 | 1 | 1 |  |  |  |  | 1 | 2 | 3 | 4 | 5
2 | Payment Gateway Failure | Payment system error prevents transactions, affecting revenue and trust. | Sadia Karim | 3 | 2 | 6 | Probability | Impact |  | 5 | 5 | 10 | 15 | 20 | 25
3 | Data Breach | Customer data (emails, card info) exposed to hackers. | Mehedi Hasan | 2 | 2 | 4 | Rare | Negligible |  | 4 | 4 | 8 | 12 | 16 | 20
4 | Delivery Delays | Logistic partners fail to deliver on time, hurting brand image. | Nusrat Jahan | 4 | 5 | 20 | Possible | Minor |  | 3 | 3 | 6 | 9 | 12 | 15
5 | Inventory Mismatch | Stock quantity errors cause overselling or order cancellations. | Fahim Reza | 5 | 4 | 20 | Unlikely | Minor |  | 2 | 2 | 4 | 6 | 8 | 10
6 | Supplier Reliability | Inconsistent suppliers cause shortage in high-demand products. | Taslima Akter | 3 | 3 | 9 | Likely | Critical |  | 1 | 1 | 2 | 3 | 4 | 5
7 | Refund & Return Fraud | Customers abuse return policies leading to financial loss. | Naimul Huda | 5 | 4 | 20 | Very Likely | Major
8 | Cyber Attack / DDoS | Malicious attacks disrupt website performance or cause downtime. | Farzana Rahman | 3 | 5 | 15 | Possible | Moderate
9 | Poor Customer Review Surge | Negative reviews spread online, reducing trust and sales. | Tanvir Chowdhury | 3 | 1 | 3 | Very Likely | Major | Probability Level | 5 4 3 2 1: Impact Level
10 | Regulatory Non-Compliance | Failure to meet e-commerce laws, taxes, or consumer rights. | Sumiya Akter | 2 | 5 | 10 | Possible | Critical | Very Likely | 5 4 3 2 1: Negligible
[7 empty] | Possible | Negligible | Likely | 5 4 3 2 1: Minor
[7 empty] | Unlikely | Critical | Possible | 5 4 3 2 1: Moderate
[9 empty] | Unlikely | 5 4 3 2 1: Major
[9 empty] | Rare | 5 4 3 2 1: Critical