## Task Tracker
Task ID | Task Name | Team | Task Owner | Start Date | Due Date | Task Duration | Status | Overdue?
1 | Update product catalog | Tech | Rakib Hossain | 2025-09-23 | 2025-10-02 | 9 | Completed | No
2 | Optimize homepage | Customer Service | Sadia Akter | 2025-09-26 | 2025-10-11 | 15 | Overdue | Yes
3 | Customer order report | Operations | Naimul Hasan | 2025-09-23 | 2025-09-29 | 6 | Completed | No
4 | Warehouse stock check | Customer Service | Sadia Akter | 2025-08-31 | 2025-09-12 | 12 | Overdue | Yes
5 | Vendor payment processing | Operations | Naimul Hasan | 2025-10-09 | 2025-10-14 | 5 | Overdue | Yes
6 | Social media campaign | Customer Service | Sadia Akter | 2025-10-09 | 2025-10-19 | 10 | Completed | No
7 | Discount coupon setup | Finance | Rupa Sultana | 2025-09-13 | 2025-09-18 | 5 | In Progress | No
8 | Delivery route planning | Marketing | Tanvir Islam | 2025-08-26 | 2025-09-04 | 9 | Pending | No
9 | Customer feedback analysis | Customer Service | Sadia Akter | 2025-09-23 | 2025-10-03 | 10 | Overdue | Yes
10 | Add new product category | Finance | Rupa Sultana | 2025-08-19 | 2025-08-30 | 11 | Overdue | Yes
11 | Price adjustment | Customer Service | Sadia Akter | 2025-09-01 | 2025-09-05 | 4 | Overdue | Yes
12 | Data cleanup | Operations | Naimul Hasan | 2025-10-08 | 2025-10-16 | 8 | Completed | No
13 | Payment gateway testing | Marketing | Tanvir Islam | 2025-09-28 | 2025-10-08 | 10 | Completed | No
14 | Sales trend report | Finance | Rupa Sultana | 2025-09-16 | 2025-09-24 | 8 | In Progress | No
15 | Return order follow-up | Marketing | Tanvir Islam | 2025-10-05 | 2025-10-09 | 4 | Overdue | Yes
16 | Inventory forecasting | Marketing | Tanvir Islam | 2025-09-14 | 2025-09-18 | 4 | Completed | No
17 | Loyalty program update | Operations | Naimul Hasan | 2025-08-13 | 2025-08-28 | 15 | In Progress | No
18 | Refund process improvement | Finance | Rupa Sultana | 2025-09-21 | 2025-09-25 | 4 | Overdue | Yes
19 | Customer segmentation | Customer Service | Sadia Akter | 2025-09-20 | 2025-10-02 | 12 | Overdue | Yes
20 | SEO optimization | Tech | Rakib Hossain | 2025-09-11 | 2025-09-22 | 11 | Completed | No
Formulas:
Overdue? = IF(OR(Table1[[#This Row],[Status]]="Overdue", AND(TODAY() > Table1[[#This Row],[Due Date]], Table1[[#This Row],[Status]] <> "Completed")), "Yes", "No")
Task Management Tracker
Overdue
Completed
In Progress
Pending
9
7
3
1

## Summary
Status | Count
Overdue | 9
Completed | 7
In Progress | 3
Pending | 1
Total | 20
Task Owners | Count
Rakib Hossain | 2
Sadia Akter | 6
Tanvir Islam | 4
Rupa Sultana | 4
Naimul Hasan | 4
Team | Count
Customer Service | 6
Operations | 4
Finance | 4
Marketing | 4
Tech | 2
Overdue | Count
Yes | 9
No | 11